## README
LotoChecker — Master Project Plan (v2 — QA-enhanced)
Single source of truth: PM • Dev • Manager — Updated weekly by PM
Sheet | Mục đích | Đối tượng đọc chính | Tần suất cập nhật
1. Project Charter | Tổng quan dự án 1 trang | Manager / Stakeholder | Khi có change request lớn
2. Roadmap | Sơ đồ tuần Gantt + QA workstream xuyên suốt | Tất cả | Khi reschedule
3. Phase Plan | Entry/exit criteria, deliverables, sign-off | Manager + PM | Khi chuyển phase
4. Screen Matrix | 37 màn hình UI với status, designer, dev | Designer, FE, QA | Hằng tuần
5. Feature Matrix | 45 features theo MoSCoW + phase | PM, Dev, QA, Manager | Khi có change request
6. API List | 45 REST/WebSocket endpoints | BE, FE, QA | Hằng tuần
7. DB Schema | Design DB for prj | FE, BE, QA | Khi có change request
8. Sprint Backlog | 65+ task chia 4 sprint (đã thêm testing) | Toàn team | Daily / mỗi standup
9. Test Strategy | Test pyramid, DoD, môi trường, tools, release checklist | PM/QA, Dev, Manager | Khi đổi quy trình
10. Bug Log | Bug tracking riêng — severity P1-P4, repro, fix | PM/QA, Dev | Khi có bug mới
Issue Log | Vấn đề non-bug: blocker, dependency, infra | PM, Tech Lead | Khi có issue mới
Risk Log | Rủi ro tiềm ẩn (review mỗi 2 tuần) | PM, Manager | Mỗi 2 tuần
Decision Log | Quyết định kỹ thuật/business quan trọng | Toàn team | Khi có decision
Weekly Report | Template báo cáo tuần cho manager | Manager | Mỗi thứ Sáu

## 1. Project Charter
LotoChecker — Project Charter
Phase 1 MVP • 2 tháng • AIoT Inc
THÔNG TIN CHUNG
Tên dự án | LotoChecker — Nền tảng phân tích xổ số Nhật Bản
Sponsor | Nguyễn Mạnh Hùng (hungnm@aiot-global.com)
PM / QA
Tech Lead
Ngày kick-off | 2026-06-10
Demo nội bộ | 2026-07-03
UAT với sponsor | Tuần 8
Soft launch | Cuối tuần 8
Team | 1 Frontend + 1 Backend + 1 PM/QA + 1 Tester
Tech stack | Next.js + TS + i18n + Tailwind· FastAPI· PostgreSQL + Redis · Docker + Vercel/AWS
MỤC TIÊU KINH DOANH (WHY)
• Lấp khoảng trống thị trường: chưa có platform phân tích frequency cho lottery Nhật.
• Tiếp cận 2 segment: người Nhật chơi xổ số + cộng đồng người Việt tại Nhật.
• Validate freemium: Free → Premium ¥500/tháng. Mục tiêu conversion 3–5% sau 3 tháng.
• Không phát sinh giao dịch tiền thật → an toàn pháp lý.
• Build nền tảng dữ liệu để mở rộng LINE Mini App Phase 2.
IN SCOPE (Phase 1 MVP) |  | OUT OF SCOPE (Phase 1)
• Auth: email + password, JWT |  | • LINE Mini App (P2)
• Chơi thử Loto 6/7/Mini |  | • Backtesting / Strategy (P2)
• Frequency analyzer realtime |  | • AI Number Generator (P2)
• Crawler Mizuho + fallback admin |  | • Push notifications (P2)
• My Page + history + leaderboard |  | • Nhóm chơi / Syndicate (P2)
• Statistics: Hot/Cold + heatmap |  | • Payment thật ( Confirm Payment) (P2 - P1 placeholder)
• Admin panel + Premium gating |  | • OAuth Google (P2)
• Responsive mobile-first |  | • Native mobile app (P3)
• Test infrastructure (unit/E2E/load) |  | • Penetration test chuyên nghiệp (P2)
• UAT với sponsor |  | • Multi-region deployment (P3)
• Multi languages
TOP 7 RISKS (xem chi tiết ở sheet 11. Risk Log)
ID | Risk | Xác suất × Tác động | Mitigation
R-01 | Mizuho Bank đổi cấu trúc HTML → crawler hỏng | Medium × High | Monitoring + alert; selector ổn định Tìm nguồn backup nếu Mizuho lỗi
R-02 | Frequency query chậm khi user concurrent tăng | Medium × High | Redis cache; pre-compute
R-04 | Conversion Free → Premium < 3% | Medium × Medium | A/B test paywall
R-05 | Team 3 người: 1 sick = slip 1 tuần | Medium × Medium | Buffer + cross-train
R-11 | PM kiêm QA = bottleneck, miss bug (mới) | High × High | Test automation > 60%; UAT có sponsor
R-13 | Data crawl ban đầu chứa lỗi (mới) | Medium × High | Validate import; cross-check source 2

## 2. Roadmap
Roadmap — 8 tuần + QA xuyên suốt
Workstream | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Owner | Status | Notes
Setup repo + CI/CD + DB schema | █ | [7 empty] | BE/PM | Not Started
Create UI-UX | █ | [7 empty] | FE/PM | Not Started
Auth module (register/login/JWT) | █ | █ | [6 empty] | BE+FE | Not Started
Data crawler (Mizuho) + initial import |  | █ | [6 empty] | BE | Not Started | 1,400+ kỳ
Admin: schedule + manual entry |  | █ | [6 empty] | BE+FE | Not Started
My Page + History + Saved sets |  | █ | [6 empty] | FE+BE | Not Started
Lottery simulation + result matching |  |  | █ | [5 empty] | BE | Not Started
UI/UX polish + i18n VI/JA |  |  | █ | [5 empty] | FE | Not Started
Frequency analyzer + Redis cache |  |  | █ | [5 empty] | BE | Not Started | Signature feature
Number picker UI + realtime counter |  |  |  | █ |  |  |  |  | FE | Not Started
MILESTONE: Demo nội bộ |  |  |  | ◆ |  |  |  |  | PM | Not Started | End W4
Leaderboard + Point system |  |  |  |  | █ |  |  |  | FE+BE | Not Started
Statistics dashboard (Hot/Cold + heatmap) | [5 empty] | █ |  |  | FE+BE | Not Started
Admin panel + Premium gating | [6 empty] | █ |  | FE+BE | Not Started
Deploy production + soft launch | [7 empty] | █ | BE+PM | Not Started
MILESTONE: UAT với sponsor | [7 empty] | ◆ | PM | Not Started
MILESTONE: Soft Launch v1.0 | [7 empty] | ◆ | PM | Not Started | End W8
─── QA WORKSTREAM (xuyên suốt) ───
[QA] Test infra setup (Jest/Pytest/Playwright/k6) | █ | [7 empty] | PM/QA + Dev | Not Started | Foundation
[QA] Unit tests (dev tự viết, theo DoD) | █ | █ | █ | █ | █ | █ | █ | █ | Dev | Not Started | Continuous
[QA] Integration & API tests |  | █ | █ | █ | █ | █ | █ | █ | PM/QA + BE | Not Started | Continuous
[QA] E2E test (Playwright) — happy paths |  |  | █ | █ | █ | █ | █ | █ | PM/QA | Not Started | Continuous
[QA] Performance test cho Frequency (P95 < 200ms) |  |  |  | █ |  | █ |  | █ | PM/QA + BE | Not Started | Verify từ Sprint 2
[QA] Cross-browser + mobile responsive test | [5 empty] | █ | █ | █ | PM/QA + FE | Not Started
[QA] Security scan (OWASP ZAP + dep audit) | [6 empty] | █ | █ | PM/QA + BE | Not Started
[QA] Bug bash + regression |  |  |  | █ |  |  | █ | █ | Toàn team | Not Started | Trước mỗi milestone
[QA] UAT formal với sponsor | [7 empty] | █ | PM + Sponsor | Not Started | Mới — 1 buổi W8
Chú thích: | █ Dev work | █ QA work | ◆ Milestone

## 3. Phase Plan
Phase Plan — Entry / Exit Criteria & Deliverables
Phase | Duration | Entry Criteria | Key Deliverables | Exit Criteria | Sign-off
0. Discovery & Setup | W1 | • Kickoff done • Stakeholder list xác nhận • Tech stack thống nhất | • Repo + CI/CD • ERD + DB migration v1 • Project plan • Figma workspace • Testing framework (Jest/Pytest/Playwright/k6) • Definition of Done document | • Dev env chạy được • 1 commit pass CI (lint + test + build) • DoD checklist approved | PM + Tech Lead
1. Foundation (Auth + Data) | W1–W2 | • Phase 0 done • DB schema approved | • Auth module (register/login/JWT) • Crawler Mizuho OK • 1,400+ kỳ đã import + validate • Admin entry UI • Unit test coverage > 70% cho module | • User register + login OK • Crawler chạy auto 3 ngày 0 lỗi • Data spot-check 10% pass • Unit + integration test xanh | PM
2. Core Engine (Sim + Frequency) | W3–W4 | • Phase 1 done • Lottery data sạch | • Submit play + đối chiếu kết quả • Frequency engine + Redis cache • Number picker UI realtime • Performance test baseline (Frequency) • E2E test: Auth + Play flows | • Frequency P95 < 200ms verified • E2E test xanh • Demo nội bộ pass • Anh Hùng review pass • 0 P1 bug | Sponsor (anh Hùng)
3. Engagement Layer | W5–W6 | • Phase 2 done + demo pass | • My Page + History • Saved sets CRUD • Leaderboard + Points • Statistics dashboard • Cross-browser test • Mobile responsive verified | • User journey end-to-end mượt • Charts render < 1s • Cross-browser test pass (Chrome/Safari/Firefox) • Mobile test pass • 0 P1 bug | PM + Sponsor
4. Monetization + Launch | W7–W8 | • Phase 3 done | • Admin panel • Premium gating đầy đủ • UI/UX polish + i18n • Production deploy + monitoring • Security scan (OWASP ZAP) pass • Load test (100 RPS) pass • UAT formal với sponsor | • 0 P1 bug, ≤ 3 P2 bug • Lighthouse > 80 • Security scan: 0 high vuln • Load test: P95 < 300ms • UAT sign-off từ sponsor • Rollback drill OK | Sponsor (anh Hùng)
5. Hypercare (Post-launch) | W9+ (2 tuần) | • Soft launch done | • Daily monitoring • Bug fix hotline (< 4h cho P1) • User feedback loop • Phase 2 backlog • Postmortem ngày 7 | • Crash-free > 99% • Bug P1 < 24h resolve • Phase 2 plan approved | PM

## 4. Screen Matrix
Screen Matrix — All Screens
ID | Module | Screen | Note | User Role | Priority | Phase | Designer | FE Dev | QA | Status | Link (Figma / Jira) | Date Start | Hours | Comments
S-001 | Public | Landing Page | Giới thiệu LotoChecker + CTA đăng ký | Guest | Must | P1 |  |  |  | Not Started
S-002 | Public | Pricing Page | Bảng so sánh Free vs Premium ¥500/月 | Guest | Must | P1 |  |  |  | Not Started
S-010 | Auth | Register | Form đăng ký email + password | Guest | Must | P1 |  |  |  | Not Started
S-011 | Auth | Email Verification | Trang xác nhận sau khi click link email | Guest | Must | P1 |  |  |  | Not Started
S-012 | Auth | Login | Form đăng nhập + Remember me | Guest | Must | P1 |  |  |  | Not Started
S-013 | Auth | Forgot Password | Form nhập email gửi reset link | Guest | Must | P1 |  |  |  | Not Started
S-014 | Auth | Reset Password | Form set new password từ link email | Guest | Must | P1 |  |  |  | Not Started
S-020 | App | Home / Dashboard | Tổng quan: kỳ sắp tới, hot numbers, CTA | User | Must | P1 |  |  |  | Not Started
S-021 | Play | Play — Loto 6 | Chọn 6/43. Realtime frequency counter. | User | Must | P1 |  |  |  | Not Started
S-022 | Play | Play — Loto 7 | Chọn 7/37. Realtime frequency counter. | User | Must | P1 |  |  |  | Not Started
S-023 | Play | Play — Mini Loto | Chọn 5/31. Realtime frequency counter. | User | Must | P1 |  |  |  | Not Started
S-024 | Play | Submit Confirmation | Xác nhận lưu bộ số + ngày quay | User | Must | P1 |  |  |  | Not Started
S-030 | Profile | My Page | Info user + tổng điểm + xếp hạng | User | Must | P1 |  |  |  | Not Started
S-031 | Profile | Edit Profile | Sửa tên, avatar, ngôn ngữ | User | Should | P1 |  |  |  | Not Started
S-032 | Profile | Change Password | Đổi mật khẩu (yêu cầu pass cũ) | User | Should | P1 |  |  |  | Not Started
S-033 | History | Play History | List các lần chơi + kết quả đối chiếu | User | Must | P1 |  |  |  | Not Started
S-034 | History | Play History Detail | Chi tiết 1 lần chơi: số đã chọn vs trúng | User | Must | P1 |  |  |  | Not Started
S-040 | Saved Sets | Saved Sets List | List bộ số đã lưu | User | Should | P1 |  |  |  | Not Started
S-041 | Saved Sets | Add / Edit Saved Set | Tạo/sửa bộ số yêu thích | User | Should | P1 |  |  |  | Not Started
S-050 | Social | Leaderboard | Top user theo điểm. Free: top 10. | User | Must | P1 |  |  |  | Not Started
S-060 | Results | Lottery Result History | Timeline 1,400+ kỳ. Tìm theo ngày/số. | User | Must | P1 |  |  |  | Not Started
S-061 | Results | Lottery Result Detail | Chi tiết 1 kỳ: số trúng, jackpot, winners | User | Must | P1 |  |  |  | Not Started
S-070 | Statistics | Stats Dashboard (overview) | Tổng hợp hot/cold + phân phối | User | Must | P1 |  |  |  | Not Started
S-071 | Statistics | Hot / Cold Numbers | Số nóng/lạnh 30/90/365 kỳ. Free: cơ bản. | User | Must | P1 |  |  |  | Not Started
S-072 | Statistics | Distribution Stats | Chẵn/lẻ, tổng, khoảng cách | User | Should | P1 |  |  |  | Not Started
S-073 | Statistics | Heatmap View (Premium) | Heatmap màu sắc theo tần suất. | Premium | Should | P1 |  |  |  | Not Started
S-080 | Premium | Premium Upgrade Page | Giới thiệu Premium | User | Must | P1 |  |  |  | Not Started
S-081 | Premium | Subscription Management | Hủy / gia hạn / xem invoice | Premium | Should | P2 |  |  |  | Not Started
S-090 | Notifications | Notification Center | List thông báo basic. | User | Could | P1 |  |  |  | Not Started
S-091 | Notifications | Notification Settings | Bật/tắt push, email per category | User | Could | P2 |  |  |  | Not Started
S-099 | System | 404 / Error Pages | Not Found, Server Error, Maintenance | All | Must | P1 |  |  |  | Not Started
S-100 | Admin | Admin Login | Login riêng cho admin (RBAC) | Admin | Must | P1 |  |  |  | Not Started
S-101 | Admin | Admin Dashboard | Tổng quan: user, premium, results | Admin | Must | P1 |  |  |  | Not Started
S-102 | Admin | User Management | List user, search, suspend, đổi role | Admin | Must | P1 |  |  |  | Not Started
S-103 | Admin | Lottery Result Management | CRUD kết quả (fallback crawler) | Admin | Must | P1 |  |  |  | Not Started
S-104 | Admin | Crawler Status & Logs | Trạng thái cron, log lỗi, trigger | Admin | Should | P1 |  |  |  | Not Started
S-105 | Admin | Premium / Subscription Mgmt | List premium, doanh thu, hủy gói | Admin | Should | P1 |  |  |  | Not Started

## 5. Feature Matrix
Feature Matrix
ID | Module | Feature | Note / Acceptance Criteria | Tier | Priority | Phase | Owner | Complexity | Status | Linked Screen
F-001 | Docs | Swagger UI (/docs) | Create swagger for API |  | Must | P1 | BE | M | Not Started
F-002 | Auth | Đăng ký bằng email | User nhập email + password, verify email mới login được. | Free | Must | P1 | BE+FE | M | Not Started | S-010, S-011
F-003 | Auth | Đăng nhập + JWT + Remember Me | Login trả JWT access+refresh. | Free | Must | P1 | BE+FE | M | Not Started | S-012
F-004 | Auth | Quên / Reset password | The OTP code will expire in 5 minutes. | Free | Must | P1 | BE+FE | M | Not Started | S-013, S-014
F-005 | Auth | OAuth Google | Phase 2. | Free | Could | P2 | BE+FE | M | Not Started | S-012
F-010 | Play | Chơi thử Loto 6 (1-43) | Chọn 6 số khác nhau, submit, chờ đối chiếu. | Free | Must | P1 | FE+BE | L | Not Started | S-021
F-011 | Play | Chơi thử Loto 7 (1-37) | Chọn 7 số khác nhau. | Free | Must | P1 | FE+BE | L | Not Started | S-022
F-012 | Play | Chơi thử Mini Loto (1-31) | Chọn 5 số khác nhau. | Free | Must | P1 | FE+BE | L | Not Started | S-023
F-013 | Play | Giới hạn 3 lần/kỳ (Free) | Free max 3 submit/kỳ. Premium unlimited. Không được chọn kỳ chơi, chỉ được chơi kỳ tiếp theo. Premium không giới hạn kỳ, lượt. | Free/Prem | Must | P1 | BE | S | Not Started | S-021..023
F-014 | Play | Lưu bộ số yêu thích | Free: 1 set. Premium: không giới hạn. | Free/Prem | Should | P1 | FE+BE | M | Not Started | S-040, S-041
F-015 | Play | Chơi lại bộ số đã lưu (1 click) | Click 'Play again' → fill bộ cũ. | Free/Prem | Should | P1 | FE | S | Not Started | S-040
F-020 | Frequency | Realtime frequency counter | Subset query {s1..sn}, P95 < 200ms. | Free/Prem | Must | P1 | BE+FE | XL | Not Started | S-021..023
F-021 | Frequency | Free: tối đa 3 số chọn | Free user max 3 số, blur sau đó. | Free | Must | P1 | BE+FE | S | Not Started | S-021..023
F-022 | Frequency | Premium: full 6 số | Premium full frequency. Maybe 4 or 5. | Premium | Must | P1 | BE+FE | S | Not Started | S-021..023
F-023 | Frequency | Redis cache hot combos | Cache top 1000, TTL 24h. | — | Must | P1 | BE | M | Not Started | —
F-030 | Stats | Hot / Cold numbers | 30/90/365 kỳ. Free: cơ bản. | Free/Prem | Must | P1 | BE+FE | M | Not Started | S-071
F-031 | Stats | Phân phối chẵn/lẻ | Tỷ lệ chẵn/lẻ kỳ trúng giải. | Free | Should | P1 | BE+FE | S | Not Started | S-072
F-032 | Stats | Phân phối tổng số | Histogram tổng. TB ~132 Loto 6. | Free | Should | P1 | BE+FE | S | Not Started | S-072
F-033 | Stats | Heatmap (Premium) | Heatmap màu sắc 1-43. | Premium | Should | P1 | FE | M | Not Started | S-073
F-034 | Stats | Export CSV/PDF (Premium) | Phase 2 ưu tiên thấp. | Premium | Could | P2 | BE+FE | M | Not Started | S-070
F-040 | Results | Lịch sử kết quả xổ số | Free: 30 kỳ. Premium: full. | Free/Prem | Must | P1 | BE+FE | M | Not Started | S-060
F-041 | Results | Tìm kiếm kỳ quay | Filter ngày, số, tổ hợp. | Free/Prem | Must | P1 | BE+FE | M | Not Started | S-060
F-042 | Results | Lịch quay sắp tới | 3 loại. | Free/Prem | Must | P1 | BE+FE | S | Not Started | S-020
F-050 | Crawler | Auto-fetch Mizuho | Cron hằng ngày sau giờ quay. | — | Must | P1 | BE | L | Not Started | —
F-051 | Crawler | Admin nhập tay fallback | UI khi crawler fail. | Admin | Must | P1 | FE+BE | M | Not Started | S-103
F-052 | Crawler | Alert khi crawler fail | Email/Slack sau 2 fail liên tiếp. | Admin | Should | P1 | BE | S | Not Started | —
F-060 | Engagement | Point system | Trúng N số = X điểm. | Free/Prem | Must | P1 | BE | M | Not Started | —
F-061 | Engagement | Leaderboard | Free: top 10. Premium: full + badge. | Free/Prem | Must | P1 | BE+FE | M | Not Started | S-050
F-062 | Engagement | Badge / Achievement | Phase 2 ưu tiên. | Premium | Could | P2 | BE+FE | M | Not Started | S-050
F-070 | Premium | Upgrade flow + gating | Middleware RBAC; CTA gating. | Free/Prem | Must | P1 | BE+FE | L | Not Started | S-080
F-071 | Premium | Thanh toán Stripe | P1 placeholder; P2 integrate. | Premium | Should | P2 | BE+FE | L | Not Started | S-080, S-081
F-072 | Premium | Trial 7 ngày | A/B test. | Premium | Could | P2 | BE | M | Not Started | S-080
F-080 | Smart | Backtesting | Chơi bộ này 100 kỳ trúng bao nhiêu. | Premium | Should | P2 | BE+FE | L | Not Started | —
F-081 | Smart | Smart Number Generator | Theo phân phối lịch sử. | Premium | Should | P2 | BE+FE | L | Not Started | —
F-082 | Smart | Thông báo suýt trúng | Push/email khi 4/6 match. | Premium | Could | P2 | BE | M | Not Started | —
F-083 | Smart | Nhóm chơi / Syndicate | Tạo nhóm, chia sẻ. | Premium | Could | P2 | BE+FE | XL | Not Started | —
F-084 | Smart | LINE Mini App | Tích hợp LINE. | — | Should | P2 | FE+BE | XL | Not Started | —
F-090 | Admin | User management | List, suspend, đổi role. | Admin | Must | P1 | BE+FE | M | Not Started | S-102
F-091 | Admin | Lottery result CRUD | Tạo/sửa/xóa. | Admin | Must | P1 | BE+FE | M | Not Started | S-103
F-092 | Admin | Crawler control + logs | Trigger thủ công. | Admin | Should | P1 | BE+FE | S | Not Started | S-104
F-100 | NFR | Responsive mobile-first | Lighthouse > 80. | — | Must | P1 | FE | M | Not Started | All
F-101 | NFR | i18n VI / JA / EN | Default theo browser locale. | — | Must | P1 | FE | M | Not Started | All
F-102 | NFR | API P95 < 300ms | Load test 100 RPS. | — | Must | P1 | BE | M | Not Started | —
F-103 | NFR | OWASP top 10 | Rate-limit, sanitize. | — | Must | P1 | BE | M | Not Started | —
F-104 | NFR | Monitoring + logging | Sentry, alert P1. | — | Should | P1 | BE | S | Not Started | —
F-105 | NFR | Code coverage > 70% | Unit test BE + FE critical paths. (Mới) | — | Should | P1 | Dev | M | Not Started | —
F-106 | NFR | E2E happy paths covered | Playwright cho 5 user journey chính. (Mới) | — | Must | P1 | PM/QA | M | Not Started | —

## 6. API List
API List — REST + WebSocket endpoints
ID | Domain | Method | Endpoint | Note | Auth | Role | Request / Response (tóm tắt) | Sprint | Owner | Status
API-001 | Auth | POST | /api/auth/register | Đăng ký + gửi verify email | None | Guest | Req: {email, password, name} → Res: {userId, emailSentTo} | S1 | BE | Not Started
API-002 | Auth | POST | /api/auth/verify-email | Verify email bằng token | None | Guest | Req: {token} → Res: 204 | S1 | BE | Not Started
API-003 | Auth | POST | /api/auth/login | Login, trả JWT | None | Guest | Req: {email, password, rememberMe} → Res: {access, refresh, user} | S1 | BE | Not Started
API-004 | Auth | POST | /api/auth/refresh | Refresh token | Refresh JWT | User | Req: {refreshToken} → Res: {accessToken} | S1 | BE | Not Started
API-005 | Auth | POST | /api/auth/logout | Logout | JWT | User | 204 | S1 | BE | Not Started
API-006 | Auth | POST | /api/auth/forgot-password | Gửi reset link | None | Guest | Req: {email} → 204 | S1 | BE | Not Started
API-007 | Auth | POST | /api/auth/reset-password | Set new password | None | Guest | Req: {token, newPassword} → 204 | S1 | BE | Not Started
API-008 | Auth | GET | /api/auth/me | Info user hiện tại | JWT | User | Res: {id, email, name, role, isPremium, points} | S1 | BE | Not Started
API-010 | User | GET | /api/users/me | Profile chi tiết | JWT | User | Res: {profile, stats} | S3 | BE | Not Started
API-011 | User | PUT | /api/users/me | Update profile | JWT | User | Req: {name, avatar, language} | S3 | BE | Not Started
API-012 | User | PUT | /api/users/me/password | Đổi mật khẩu | JWT | User | Req: {oldPassword, newPassword} | S3 | BE | Not Started
API-020 | Lottery | GET | /api/lottery/results | List kết quả | JWT (opt) | All | Query: type, dateFrom, dateTo, page, limit | S1 | BE | Not Started
API-021 | Lottery | GET | /api/lottery/results/:id | Chi tiết 1 kỳ | JWT (opt) | All | Res: {drawNo, date, numbers, jackpot, winners} | S1 | BE | Not Started
API-022 | Lottery | GET | /api/lottery/results/latest | Kỳ mới nhất | JWT (opt) | All | Query: type | S1 | BE | Not Started
API-023 | Lottery | GET | /api/lottery/schedule | Lịch quay | None | All | Res: [{type, nextDrawDate}] | S1 | BE | Not Started
API-030 | Play | POST | /api/plays | Submit bộ số | JWT | User | Req: {type, numbers[]} → Res: {playId, scheduledDrawDate} | S2 | BE | Not Started
API-031 | Play | GET | /api/plays/me | Lịch sử chơi | JWT | User | Query: page, limit, type | S3 | BE | Not Started
API-032 | Play | GET | /api/plays/:id | Chi tiết 1 lần chơi | JWT | User | Res: {numbers, drawResult, matchCount, pointsEarned} | S3 | BE | Not Started
API-040 | Frequency | POST | /api/frequency/check | Subset query — signature feature | JWT | User | Req: {type, numbers[]} → Res: {count, lastSeenDraws[]} | S2 | BE | Not Started
API-041 | Frequency | GET | /api/frequency/single | Tần suất 1 số | JWT | User | Query: type, number | S2 | BE | Not Started
API-042 | Frequency | WS | /ws/frequency | Live counter (polling fallback) | JWT | User | Stream: {numbers[], count} | S2 | BE | Not Started
API-050 | Stats | GET | /api/stats/hot-cold | Hot/cold | JWT | User | Query: type, period=30¦90¦365 | S3 | BE | Not Started
API-051 | Stats | GET | /api/stats/distribution | Chẵn/lẻ, tổng, khoảng cách | JWT | User | Query: type | S3 | BE | Not Started
API-052 | Stats | GET | /api/stats/heatmap | Heatmap (Premium) | JWT | Premium | Query: type, period | S3 | BE | Not Started
API-060 | SavedSets | GET | /api/saved-sets | List bộ số | JWT | User | Free: max 1 | S3 | BE | Not Started
API-061 | SavedSets | POST | /api/saved-sets | Tạo bộ số | JWT | User | Req: {name, type, numbers[]} | S3 | BE | Not Started
API-062 | SavedSets | PUT | /api/saved-sets/:id | Sửa bộ số | JWT | User | Req: {name, numbers[]} | S3 | BE | Not Started
API-063 | SavedSets | DELETE | /api/saved-sets/:id | Xóa bộ số | JWT | User | 204 | S3 | BE | Not Started
API-070 | Leaderboard | GET | /api/leaderboard | Bảng xếp hạng | JWT (opt) | All | Query: period. Free: top 10 | S3 | BE | Not Started
API-071 | Points | GET | /api/points/me | Tổng điểm + history | JWT | User | Res: {total, history[]} | S3 | BE | Not Started
API-080 | Premium | GET | /api/premium/status | Trạng thái sub | JWT | User | Res: {isPremium, expireAt, plan} | S4 | BE | Not Started
API-081 | Premium | POST | /api/premium/subscribe | Đăng ký Premium | JWT | User | P1 placeholder | S4 | BE | Not Started
API-082 | Premium | POST | /api/premium/cancel | Hủy sub | JWT | Premium | Res: {cancelAt} | S4 | BE | Not Started
API-090 | Notif | GET | /api/notifications | List thông báo | JWT | User | Query: page, limit, unreadOnly | S4 | BE | Not Started
API-091 | Notif | PUT | /api/notifications/:id/read | Mark read | JWT | User | 204 | S4 | BE | Not Started
API-100 | Admin | GET | /api/admin/dashboard | Thống kê tổng quan | JWT | Admin | Res: {userCount, premiumCount, latestResults, crawlerStatus} | S4 | BE | Not Started
API-101 | Admin | GET | /api/admin/users | List user | JWT | Admin | Query: page, limit, search, role | S4 | BE | Not Started
API-102 | Admin | PUT | /api/admin/users/:id | Update user | JWT | Admin | Req: {status, role} | S4 | BE | Not Started
API-103 | Admin | POST | /api/admin/lottery-results | Nhập tay | JWT | Admin | Req: {type, drawNo, date, numbers, jackpot} | S1 | BE | Not Started
API-104 | Admin | PUT | /api/admin/lottery-results/:id | Sửa kết quả | JWT | Admin | Req: {numbers, jackpot} | S1 | BE | Not Started
API-105 | Admin | DELETE | /api/admin/lottery-results/:id | Xóa kết quả | JWT | Admin | 204 | S1 | BE | Not Started
API-106 | Admin | POST | /api/admin/crawler/trigger | Trigger crawler | JWT | Admin | Res: {jobId, status} | S1 | BE | Not Started
API-107 | Admin | GET | /api/admin/crawler/logs | Log crawler | JWT | Admin | Query: page, limit, status | S1 | BE | Not Started
API-108 | Admin | GET | /api/admin/premium/subscriptions | List sub | JWT | Admin | Query: page, status | S4 | BE | Not Started

## 7. DB Schema
Table Name |  |  | Author | Reviewer | Created Date
lottery_types
Overview
Lottery Type Master
Physical Name | Logical Name | TYPE | Length | Sample Data | NOT NULL | DEFAULT | Auto Increment | PK | FK | Comment
id | ID | SMALLSERIAL |  |  | Y |  | Y | Y |  | Primary key
code | Type code | VARCHAR | 20 | 'loto6', 'loto7', 'mini' | [5 empty] | UNIQUE
number_range_max | Max number value | SMALLINT |  | 43, 37, 31
numbers_per_draw | Numbers per draw | SMALLINT |  | 6, 7, 5
bonus_count | Bonus number count | SMALLINT |  | 1, 2, 1
DDL
CREATE TABLE lottery_types ( id SMALLSERIAL PRIMARY KEY, code VARCHAR(20) UNIQUE, -- 'loto6', 'loto7', 'mini' number_range_max SMALLINT, -- 43, 37, 31 numbers_per_draw SMALLINT, -- 6, 7, 5 bonus_count SMALLINT -- 1, 2, 1 );
Table Name |  |  | Author | Reviewer | Created Date
draws
Overview
Draw results (per lottery round)
Physical Name | Logical Name | TYPE | Length | Sample Data | NOT NULL | DEFAULT | Auto Increment | PK | FK | Comment
id | ID | BIGSERIAL |  |  | Y |  | Y | Y |  | Primary key
lottery_type_id | Lottery type ID | SMALLINT | [6 empty] | lottery_types(id)
draw_number | Draw number (round) | INT |  |  | Y |  |  |  |  | UNIQUE (lottery_type_id, draw_number)
drawn_at | Drawn date | DATE |  |  | Y
venue | Venue | VARCHAR | 100 | Tokyo Takarakuji Dream Hall
numbers | Winning numbers | SMALLINT[] |  | {1,6,17,27,34,43} | Y |  |  |  |  | GIN index applied
bonus_numbers | Bonus numbers | SMALLINT[] | [7 empty] | Loto6:1, Loto7:2, Mini:1
carryover_yen | Carryover amount | BIGINT |  |  |  | 0 |  |  |  | Unit: JPY
total_sales_yen | Total sales | BIGINT | [7 empty] | Unit: JPY
payment_period_start | Payment period start | DATE
payment_period_end | Payment period end | DATE
source | Data source | VARCHAR | 50 | 'mizuho', 'manual'
raw_html | Raw HTML | TEXT | [7 empty] | Snapshot for debugging
DDL
CREATE TABLE draws ( id BIGSERIAL PRIMARY KEY, lottery_type_id SMALLINT REFERENCES lottery_types(id), draw_number INT NOT NULL, drawn_at DATE NOT NULL, venue VARCHAR(100), -- Drawing venue numbers SMALLINT[] NOT NULL, -- e.g., {1,6,17,27,34,43} bonus_numbers SMALLINT[], -- Loto6:1, Loto7:2, Mini:1 carryover_yen BIGINT DEFAULT 0, -- Carryover total_sales_yen BIGINT, -- Total sales payment_period_start DATE, -- Payment period start payment_period_end DATE, -- Payment period end source VARCHAR(50), -- 'mizuho', 'manual' raw_html TEXT, -- Snapshot for debug UNIQUE (lottery_type_id, draw_number) ); CREATE INDEX idx_draws_numbers_gin ON draws USING GIN (numbers);
Table Name |  |  | Author | Reviewer | Created Date
draw_prizes
Overview
Prize breakdown per draw (by tier)
Physical Name | Logical Name | TYPE | Length | Sample Data | NOT NULL | DEFAULT | Auto Increment | PK | FK | Comment
id | ID | BIGSERIAL |  |  | Y |  | Y | Y |  | Primary key
draw_id | Draw ID | BIGINT | [6 empty] | draws(id) ON DELETE CASCADE
tier | Prize tier | SMALLINT |  | 1 = 1st, 2 = 2nd ... | Y |  |  |  |  | UNIQUE (draw_id, tier)
winners_count | Number of winners | INT |  |  | Y
prize_amount_yen | Prize amount each | BIGINT |  |  | Y |  |  |  |  | Unit: JPY
DDL
CREATE TABLE draw_prizes ( id BIGSERIAL PRIMARY KEY, draw_id BIGINT REFERENCES draws(id) ON DELETE CASCADE, tier SMALLINT NOT NULL, -- 1=1st, 2=2nd, ... winners_count INT NOT NULL, -- number of winners prize_amount_yen BIGINT NOT NULL, -- amount per winner UNIQUE (draw_id, tier) );
Table Name |  |  | Author | Reviewer | Created Date
users
Overview
User accounts & authentication
Physical Name | Logical Name | TYPE | Length | Sample Data | NOT NULL | DEFAULT | Auto Increment | PK | FK | Comment
id | ID | BIGSERIAL |  |  | Y |  | Y | Y |  | Primary key
email | Email address | CITEXT |  |  | Y |  |  |  |  | UNIQUE / case-insensitive
password_hash | Password hash | TEXT
email_verified | Email verified flag | BOOLEAN |  |  |  | FALSE
role | Role | VARCHAR | 20 | 'free', 'premium', 'admin' |  | 'free'
premium_until | Premium expiry | TIMESTAMPTZ
locale | Locale | VARCHAR | 5 | 'ja', 'en' ... |  | 'ja'
created_at | Created at | TIMESTAMPTZ |  |  |  | NOW()
DDL
CREATE TABLE users ( id BIGSERIAL PRIMARY KEY, email CITEXT UNIQUE NOT NULL, password_hash TEXT, email_verified BOOLEAN DEFAULT FALSE, role VARCHAR(20) DEFAULT 'free', -- 'free', 'premium', 'admin' premium_until TIMESTAMPTZ, locale VARCHAR(5) DEFAULT 'ja', created_at TIMESTAMPTZ DEFAULT NOW() );
Table Name |  |  | Author | Reviewer | Created Date
user_plays
Overview
User play history (challenges)
Physical Name | Logical Name | TYPE | Length | Sample Data | NOT NULL | DEFAULT | Auto Increment | PK | FK | Comment
id | ID | BIGSERIAL |  |  | Y |  | Y | Y |  | Primary key
user_id | User ID | BIGINT | [6 empty] | users(id)
lottery_type_id | Lottery type ID | SMALLINT | [6 empty] | lottery_types(id) | Implicit reference
chosen_numbers | Chosen numbers | SMALLINT[] |  | {3,12,19,22,30,41} | Y
draw_id | Reference draw ID | BIGINT | [6 empty] | draws(id) | Draw to compare against
match_count | Match count | SMALLINT
matched_tier | Matched Tier | SMALLINT
points_earned | Points earned | INT
played_at | Played at | TIMESTAMPTZ |  |  |  | NOW()
matched_at | Matched at | TIMESTAMPTZ
DDL
CREATE TABLE user_plays ( id BIGSERIAL PRIMARY KEY, user_id BIGINT REFERENCES users(id), lottery_type_id SMALLINT REFERENCES lottery_types(id), chosen_numbers SMALLINT[] NOT NULL, draw_id BIGINT REFERENCES draws(id), -- NULL = chưa quay, filled sau khi match match_count SMALLINT, -- NULL = chưa đối chiếu matched_tier SMALLINT, -- NULL, hoặc 1~6 (hạng trúng) points_earned INT DEFAULT 0, played_at TIMESTAMPTZ DEFAULT NOW(), matched_at TIMESTAMPTZ -- thời điểm đối chiếu );
Table Name |  |  | Author | Reviewer | Created Date
saved_sets
Overview
User-saved number sets
Physical Name | Logical Name | TYPE | Length | Sample Data | NOT NULL | DEFAULT | Auto Increment | PK | FK | Comment
id | ID | BIGSERIAL |  |  | Y |  | Y | Y |  | Primary key
user_id | User ID | BIGINT | [6 empty] | users(id)
lottery_type_id | Lottery type ID | SMALLINT | [6 empty] | lottery_types(id) | Implicit reference
name | Set name | VARCHAR | 100 | My Favorite 1
numbers | Numbers | SMALLINT[]
created_at | Created at | TIMESTAMPTZ |  |  |  | NOW()
DDL
CREATE TABLE saved_sets ( id BIGSERIAL PRIMARY KEY, user_id BIGINT REFERENCES users(id), lottery_type_id SMALLINT, name VARCHAR(100), numbers SMALLINT[], created_at TIMESTAMPTZ DEFAULT NOW() );
Table Name |  |  | Author | Reviewer | Created Date
point_ledger
Overview
Point ledger (for leaderboard)
Physical Name | Logical Name | TYPE | Length | Sample Data | NOT NULL | DEFAULT | Auto Increment | PK | FK | Comment
id | ID | BIGSERIAL |  |  | Y |  | Y | Y |  | Primary key
user_id | User ID | BIGINT | [6 empty] | users(id)
delta | Point delta | INT |  | +10 / -5 | [5 empty] | Positive = add, negative = subtract
reason | Reason | VARCHAR | 50 | 'play_match', 'bonus' ...
ref_play_id | Referenced play ID | BIGINT | [7 empty] | References user_plays.id (optional)
created_at | Created at | TIMESTAMPTZ |  |  |  | NOW()
DDL
CREATE TABLE point_ledger ( id BIGSERIAL PRIMARY KEY, user_id BIGINT REFERENCES users(id), delta INT, reason VARCHAR(50), ref_play_id BIGINT, created_at TIMESTAMPTZ DEFAULT NOW() );
Table Name |  |  | Author | Reviewer | Created Date
subscriptions
Overview
Premium subscriptions (Stripe)
Physical Name | Logical Name | TYPE | Length | Sample Data | NOT NULL | DEFAULT | Auto Increment | PK | FK | Comment
id | ID | BIGSERIAL |  |  | Y |  | Y | Y |  | Primary key
user_id | User ID | BIGINT | [6 empty] | users(id)
stripe_sub_id | Stripe subscription ID | VARCHAR | 100 | sub_xxxxxxxxxxxxxx | [5 empty] | Stripe-side ID
status | Status | VARCHAR | 20 | 'active', 'canceled', 'past_due' ...
current_period_end | Current period end | TIMESTAMPTZ
created_at | Created at | TIMESTAMPTZ |  |  |  | NOW()
DDL
CREATE TABLE subscriptions ( id BIGSERIAL PRIMARY KEY, user_id BIGINT REFERENCES users(id), stripe_sub_id VARCHAR(100), status VARCHAR(20), current_period_end TIMESTAMPTZ, created_at TIMESTAMPTZ DEFAULT NOW() );

## 8. Sprint Backlog
Sprint Backlog — 4 sprint × 2 tuần
Task ID | Sprint | Module | Task | Type | Linked (Feature/Screen/API) | Assignee | Story Pt | Status | % Done | Notes
T-001 | S1 | Setup | Setup monorepo (FE + BE), conventional commits | Infra | — | BE | 3 | Not Started | 0
T-002 | S1 | Setup | Dockerize FE + BE + Postgres + Redis | Infra | — | BE | 3 | Not Started | 0
T-003 | S1 | Setup | CI/CD: GitHub Actions (lint + test + build) | Infra | — | BE | 3 | Not Started | 0
T-004 | S1 | DB | ERD + migration v1 (user, results, plays, sets) | Backend | — | BE | 5 | Not Started | 0
T-005 | S1 | Auth-BE | Register API + verify token | Backend | F-001, API-001, API-002 | BE | 3 | Not Started | 0
T-006 | S1 | Auth-BE | Login + JWT + Remember Me | Backend | F-002, API-003, API-004 | BE | 3 | Not Started | 0
T-007 | S1 | Auth-BE | Forgot/Reset password | Backend | F-003, API-006, API-007 | BE | 3 | Not Started | 0
T-008 | S1 | Auth-FE | Register + Email verification screens | Frontend | S-010, S-011 | FE | 3 | Not Started | 0
T-009 | S1 | Auth-FE | Login + Forgot/Reset screens | Frontend | S-012, S-013, S-014 | FE | 3 | Not Started | 0
T-010 | S1 | Crawler | Crawler Mizuho (Loto 6/7/Mini) + cron | Backend | F-050 | BE | 5 | Not Started | 0 | mizuhobank.co.jp
T-011 | S1 | Crawler | Initial import 1,400+ kỳ + validate | Backend | F-050 | BE | 3 | Not Started | 0 | Spot-check 10%
T-012 | S1 | Admin | Admin API nhập tay (CRUD) | Backend | F-051, API-103..105 | BE | 3 | Not Started | 0
T-013 | S1 | Admin | Admin UI: lottery result management | Frontend | S-103 | FE | 3 | Not Started | 0
T-Q01 | S1 | [QA] | Setup testing framework: Jest (FE), Pytest (BE), Playwright, k6 | QA | — | PM/QA + Dev | 3 | Not Started | 0 | Foundation. CI tự chạy
T-Q02 | S1 | [QA] | Setup staging environment + seed test data | QA | — | PM/QA + BE | 3 | Not Started | 0 | Domain
T-Q03 | S1 | [QA] | Viết Definition of Done + bug severity guideline + PR checklist | QA | — | PM/QA | 2 | Not Started | 0 | Reference: sheet 8
T-Q04 | S1 | [QA] | Unit test: Auth module (BE) — coverage > 80% | QA | F-001..003, F-105 | BE | 2 | Not Started | 0 | DoD: every API has unit test
T-Q05 | S1 | [QA] | Integration test: Crawler + import flow | QA | F-050, T-010 | PM/QA + BE | 2 | Not Started | 0
T-Q06 | S1 | [QA] | Smoke test Sprint 1 + sign-off | QA | — | PM/QA | 2 | Not Started | 0
T-020 | S2 | Play-BE | POST /plays + validate (rule chọn số) | Backend | F-010..012, API-030 | BE | 3 | Not Started | 0
T-021 | S2 | Play-BE | Cron đối chiếu kết quả + tính match | Backend | F-010..012, F-060 | BE | 3 | Not Started | 0
T-022 | S2 | Play-BE | Point system v1 + persist history | Backend | F-060 | BE | 3 | Not Started | 0
T-023 | S2 | Play-FE | Picker Loto 6 (number picker UI) | Frontend | S-021 | FE | 5 | Not Started | 0
T-024 | S2 | Play-FE | Reuse picker cho Loto 7 + Mini | Frontend | S-022, S-023 | FE | 3 | Not Started | 0
T-025 | S2 | Play-FE | Free tier limit 3 lần/ngày (FE + BE) | Full | F-013 | FE+BE | 2 | Not Started | 0
T-026 | S2 | Freq-BE | Subset query algorithm (Combination Frequency Engine) | Backend | F-020, API-040 | BE | 5 | Not Started | 0 | Target P95 < 200ms
T-027 | S2 | Freq-BE | Redis cache hot combos (top 1000) + TTL | Backend | F-023 | BE | 3 | Not Started | 0
T-028 | S2 | Freq-FE | Realtime counter trong picker | Frontend | F-020 | FE | 5 | Not Started | 0 | Polling fallback
T-029 | S2 | Freq-FE | Free vs Premium gating ở picker (blur sau 3 số) | Frontend | F-021, F-022 | FE | 2 | Not Started | 0
T-Q07 | S2 | [QA] | Unit test: Frequency engine — CRITICAL signature feature | QA | F-020, F-105 | BE | 3 | Not Started | 0 | Edge: empty, dup, out-of-range
T-Q08 | S2 | [QA] | Performance test baseline: Frequency endpoint | QA | F-020, F-102 | PM/QA + BE | 3 | Not Started | 0 | k6: 50 RPS, verify P95 < 200ms
T-Q09 | S2 | [QA] | E2E test: Auth happy path (Playwright) | QA | F-001..003, F-106 | PM/QA | 2 | Not Started | 0
T-Q10 | S2 | [QA] | E2E test: Play submission + đối chiếu (Loto 6) | QA | F-010, F-106 | PM/QA | 3 | Not Started | 0
T-Q11 | S2 | [QA] | Edge case test: invalid numbers, network drop, concurrent submit | QA | F-010..013 | PM/QA | 2 | Not Started | 0
T-Q12 | S2 | [QA] | Regression test Sprint 1 + Bug bash trước demo | QA | — | Toàn team | 3 | Not Started | 0 | 1 buổi bug bash
T-030 | S2 | Demo | Chuẩn bị demo nội bộ tuần 4 + slide tổng kết | PM | — | PM | 2 | Not Started | 0 | MILESTONE
T-040 | S3 | Profile | My Page + Edit profile + Change password | Full | S-030..032, API-010..012 | FE+BE | 5 | Not Started | 0
T-041 | S3 | History | Play History + Detail + filter | Full | S-033, S-034, API-031, 032 | FE+BE | 5 | Not Started | 0
T-042 | S3 | SavedSets | Saved sets CRUD + UI | Full | F-014, S-040, S-041 | FE+BE | 5 | Not Started | 0
T-043 | S3 | Leaderb | Leaderboard API + UI | Full | F-061, S-050, API-070 | FE+BE | 3 | Not Started | 0
T-044 | S3 | Stats-BE | Hot/Cold + Distribution API | Backend | F-030..032, API-050, 051 | BE | 5 | Not Started | 0
T-045 | S3 | Stats-FE | Stats dashboard UI | Frontend | S-070..S-072 | FE | 5 | Not Started | 0
T-046 | S3 | Stats-FE | Heatmap visualization (Premium) | Frontend | F-033, S-073, API-052 | FE | 3 | Not Started | 0
T-047 | S3 | Lottery | Lottery Result History + Detail + search | Frontend | S-060, S-061, API-020..022 | FE | 3 | Not Started | 0
T-Q13 | S3 | [QA] | Unit test: Stats calculations (hot/cold, distribution) | QA | F-030..032, F-105 | BE | 2 | Not Started | 0
T-Q14 | S3 | [QA] | E2E test: Full user journey (signup→play→history→leaderboard) | QA | F-106 | PM/QA | 3 | Not Started | 0
T-Q15 | S3 | [QA] | Cross-browser test (Chrome / Safari / Firefox) | QA | F-100 | PM/QA + FE | 3 | Not Started | 0 | Manual + BrowserStack
T-Q16 | S3 | [QA] | Mobile responsive test trên thiết bị thật (iOS/Android) | QA | F-100 | PM/QA + FE | 3 | Not Started | 0
T-Q17 | S3 | [QA] | Visual regression test cho charts + heatmap (Percy/Chromatic) | QA | F-033 | PM/QA + FE | 2 | Not Started | 0
T-Q18 | S3 | [QA] | Bug bash + regression Sprint 1+2+3 | QA | — | Toàn team | 3 | Not Started | 0
T-050 | S4 | Admin | Admin Dashboard + User Management | Full | F-090, S-101, S-102 | FE+BE | 5 | Not Started | 0
T-051 | S4 | Admin | Crawler Status & Logs UI | Full | F-092, S-104 | FE+BE | 3 | Not Started | 0
T-052 | S4 | Premium | Premium gating middleware (RBAC + per-feature) | Backend | F-070 | BE | 3 | Not Started | 0
T-053 | S4 | Premium | Premium upgrade flow (UI placeholder) | Full | F-070, S-080, S-081 | FE+BE | 5 | Not Started | 0 | Payment thật P2
T-054 | S4 | Notif | Notification Center basic | Full | S-090, API-090, API-091 | FE+BE | 3 | Not Started | 0
T-055 | S4 | Polish | UI/UX polish + responsive review | Frontend | F-100 | FE | 3 | Not Started | 0
T-056 | S4 | i18n | i18n VI/JA | Frontend | F-101 | FE | 3 | Not Started | 0
T-057 | S4 | Infra | Production deploy (Vercel + AWS/Render) + domain + SSL | Infra | — | BE | 3 | Not Started | 0
T-058 | S4 | Infra | Monitoring: Sentry + uptime + alerts | Infra | F-104 | BE | 2 | Not Started | 0
T-Q19 | S4 | [QA] | Regression Premium gating: cover toàn bộ 11 mục Free vs Premium | QA | F-070, F-013..014..021.. | PM/QA | 3 | Not Started | 0 | Critical for revenue
T-Q20 | S4 | [QA] | Load test: 100 RPS Frequency + 50 RPS các endpoint còn lại | QA | F-102 | PM/QA + BE | 3 | Not Started | 0 | k6 / Locust
T-Q21 | S4 | [QA] | Security scan: OWASP ZAP + dependency audit (npm/pip) | QA | F-103 | PM/QA + BE | 3 | Not Started | 0 | 0 high vuln
T-Q22 | S4 | [QA] | i18n test (VI + JA): text overflow, encoding, date/number format | QA | F-101 | PM/QA + FE | 2 | Not Started | 0 | Native JP reviewer 1 buổi
T-Q23 | S4 | [QA] | UAT formal với sponsor (anh Hùng) — 1 buổi + recorder | QA | — | PM + Sponsor | 3 | Not Started | 0 | MILESTONE. Sign-off required
T-Q24 | S4 | [QA] | Production smoke test sau deploy (15 min checklist) | QA | — | PM/QA | 2 | Not Started | 0
T-Q25 | S4 | [QA] | Rollback drill: rollback prod về v0, restore data, verify | QA | — | BE + PM | 2 | Not Started | 0 | Trước go-live 1 ngày
T-059 | S4 | QA | Final bug bash + bug fix sprint | Dev | — | Toàn team | 5 | Not Started | 0
T-061 | S4 | Launch | Soft launch v1.0 + monitor 48h hypercare | PM | — | PM | 2 | Not Started | 0 | MILESTONE
[6 empty] | TỔNG STORY POINTS: | 214
[6 empty] | DONE STORY POINTS: | 0
[6 empty] | % TIẾN ĐỘ TOÀN DỰ ÁN: | 0%
[6 empty] | QA STORY POINTS: | 128
[6 empty] | % QA / TỔNG: | 59.81%

## 9. Test Strategy
Test Strategy — pyramid, DoD, environments, release checklist
1. TEST PYRAMID — phân bổ effort & quy mô
Layer | Tỷ trọng test | Tool | Tốc độ chạy | Owner | Khi nào chạy
Unit tests | ~65% (nhiều nhất, nhanh nhất) | Jest (FE) / Pytest (BE) | Giây | Dev tự viết theo DoD | Mỗi commit, CI
Integration / API tests | ~25% | Pytest + httpx / Supertest | Phút | BE + PM/QA pair | Mỗi PR, CI
E2E tests | ~10% (ít, chậm, brittle) | Playwright | Vài phút | PM/QA | Trước merge main, nightly
Performance / Load | Continuous monitor | k6 hoặc Locust | Phút–giờ | BE + PM/QA | Sprint 2 (baseline) + Sprint 4 (full)
Security scan | Mỗi PR + manual cuối phase | OWASP ZAP, npm audit, pip-audit | Phút | BE + PM/QA | Mỗi PR + cuối phase
Manual exploratory | 1 buổi/sprint | — | 1–2h/lần | PM/QA + dev rotate | Cuối mỗi sprint
UAT | 1 buổi cuối dự án | — | 1 buổi | Sponsor + PM | Sprint 4 trước go-live
2. DEFINITION OF DONE — checklist cho mỗi task
☐ Code complete và đã self-review
☐ Unit test viết và pass (coverage tăng hoặc giữ nguyên, target > 70%)
☐ Integration test viết cho API mới (nếu có)
☐ Linter pass (eslint / pylint / mypy)
☐ Đã có 1 reviewer approve PR (tối thiểu)
☐ Cập nhật API doc (Swagger/OpenAPI) nếu thay đổi endpoint
☐ Cập nhật README nếu thêm env var, migration, command mới
☐ Manual test trên staging 1 lần
☐ Acceptance criteria của story được verify
☐ Cập nhật status + % done trong sheet Sprint Backlog
☐ Không tạo P1/P2 bug mới (verify qua regression test)
3. ENVIRONMENTS — môi trường test
Env | URL pattern | Data | Auto-deploy | Ai dùng
Local | localhost:3000 / :8000 | Docker compose + seed | — | Dev
Dev/Staging | Vercel | Subset prod data (anonymized) | Mỗi merge main | PM/QA, anh Hùng review
UAT (tùy) |  | Full prod-like data | Manual trigger | Sponsor, beta user
Production |  | Real data | Manual approval | End user
4. BUG SEVERITY — phân loại để triage
Severity | Định nghĩa | Ví dụ | Response time | Phải fix trước
P1 — Critical | App down, mất data, security vuln, không thể dùng feature chính | Login 500, frequency engine sai số, data leak | < 4h | Phase exit / go-live
P2 — High | Feature chính hoạt động lỗi, có workaround | Save set không lưu, leaderboard sai thứ tự | < 24h | Phase exit
P3 — Medium | Lỗi nhỏ, UX khó chịu, edge case | Toast message sai chính tả, layout vỡ ở browser cũ | < 1 sprint | Trước launch
P4 — Low | Cosmetic, nice-to-have | Margin lệch 2px, typo nhỏ | Backlog | Có thể slip
5. TEST DATA STRATEGY
• Seed script tạo: 5 user (1 admin, 2 free, 2 premium), 100 kỳ lottery history, 20 saved sets, 50 plays
• Anonymize: replace real email bằng @example.com pattern
• Reset state: trước mỗi E2E test, gọi /api/test/reset (chỉ available trên dev/staging)
• Edge data: 1 user với 0 plays, 1 user 1000+ plays, lottery result với 0 winners, draw với jackpot kỷ lục
• Time data: kỳ quay quá khứ, hiện tại, tương lai — để test scheduling
6. RELEASE CHECKLIST — phải check 100% trước go-live
☐ Tất cả Must features: Status = Done
☐ Code coverage tổng > 70% (BE) và > 60% (FE)
☐ E2E test suite chạy xanh trên staging
☐ Performance test: P95 < 300ms, P99 < 500ms (Frequency P95 < 200ms)
☐ Security scan (OWASP ZAP): 0 high, 0 critical
☐ Dependency audit: 0 high vuln
☐ Bug count: 0 P1, ≤ 3 P2
☐ Lighthouse score: Performance > 80, Accessibility > 90
☐ Cross-browser test pass: Chrome, Safari, Firefox (mobile + desktop)
☐ i18n test pass: VI + JA, không có text overflow
☐ UAT với sponsor: sign-off
☐ Rollback drill: thử rollback về v0 thành công trên staging
☐ DB backup script chạy + verify restore được
☐ Monitoring (Sentry, uptime) đã setup + test alert
☐ DNS, SSL cert, CDN đã sẵn sàng
☐ Privacy Policy + Terms of Service published
☐ Status page / incident response process documented
☐ Hypercare schedule: ai on-call ngày 1-7?
☐ Post-launch survey + analytics tracking ready
☐ Communication plan: gửi email/Slack ai khi có incident

## 10. Bug Log
Bug Log — chi tiết bug + severity + verify
Bug ID | Date Reported | Title | Severity | Module | Reproduce Steps | Expected | Actual | Reporter | Assignee | Sprint | Status | Resolution
BUG-001 | — | Ví dụ: Frequency response > 500ms khi 50 RPS | P1 — Critical | Frequency | 1. Run k6 load test 50 RPS 2. POST /api/frequency/check with random combos | P95 < 200ms | P95 = 380ms | PM/QA | BE | S2 | New | —
THỐNG KÊ BUG: | P1 (Critical) | 2
| P2 (High) | 0
| P3 (Medium) | 0
| P4 (Low) | 0
| Open total | 1
| Fixed total | 0

## Issue Log
Issue Log — vấn đề non-bug (blocker, dependency, infra)
ID | Ngày phát hiện | Module | Mô tả vấn đề | Severity | Impact | Owner | Hạn xử lý | Status
I-001 | — | Example | Ví dụ: Mizuho website yêu cầu CAPTCHA → crawler bị chặn | High | Crawler không chạy được, phải nhập tay | BE | — | Not Started
I-002 | — | Example | Ví dụ: Designer chưa giao Figma cho admin panel → FE block | Medium | FE Sprint 4 delay | PM | — | Not Started

## Risk Log
Risk Log — rủi ro tiềm ẩn (review mỗi 2 tuần)
ID | Mô tả rủi ro | Loại | Xác suất | Tác động | Score | Mitigation | Contingency | Owner
R-01 | Mizuho Bank đổi cấu trúc HTML → crawler hỏng | Technical | Medium | High | 9 | Monitoring + alert; XPath ổn định; weekly health check | Admin nhập tay 1-2 ngày; thuê dev hotfix | BE
R-02 | Frequency subset query chậm khi concurrent user tăng | Performance | Medium | High | 9 | Redis cache; index DB; pre-compute; perf test từ Sprint 2 | Tăng cache TTL; read replica | BE
R-03 | Conversion Free → Premium < 3% | Business | Medium | Medium | 6 | A/B test paywall; trial 7 ngày; user survey | Reduce price; add Premium features | PM
R-04 | Team 3 người: 1 sick = slip 1 tuần | Resource | Medium | Medium | 6 | Buffer; cross-train code review; document đầy đủ | Hire freelancer; cắt non-Must scope | PM
R-05 | WebSocket realtime phức tạp, mobile network drop | Technical | Medium | Medium | 6 | Polling 1s fallback; reconnect logic; degraded mode | Bỏ realtime, dùng polling thuần | FE
R-06 | i18n delay (translation chất lượng JP) | Resource | Medium | Low | 3 | Native JP review; DeepL + edit; ship VI trước | Slip EN Phase 2 | FE
R-07 | Payment integration Stripe JP compliance phức tạp | Business | Medium | High | 9 | Defer Phase 2; P1 placeholder UI | Pre-order list; charge thủ công P1 | PM
R-08 | Mizuho rate-limit / chặn crawler IP | Technical | Low | Medium | 3 | Crawl 1 lần/ngày; respect robots; User-Agent đàng hoàng | Đổi IP/proxy; nhập tay | BE
R-09 | Initial data 1,400+ kỳ chứa lỗi/thiếu | Data | Medium | Medium | 6 | Validate khi import; spot-check 10%; cross-check source 2 | Manual fix; flag suspicious records | BE
R-10 | PM kiêm QA = bottleneck, miss test case (MỚI) | Quality | High | High | 12 | Test automation > 60%; bug bash team-wide; UAT có sponsor | Hire QA freelancer tuần 7-8; mở rộng beta tester | PM
R-11 | Không có UAT formal → bug lọt production (MỚI) | Quality | Medium | High | 9 | Schedule UAT 1 buổi với sponsor tuần 8; recorder lưu lại | Soft launch nội bộ 50 user trước public | PM
R-12 | Frequency engine tính sai số do edge case → mất uy tín (MỚI) | Quality | Medium | High | 9 | Unit test edge cases từ Sprint 2; manual cross-check 20 combos | Tạm tắt feature; rollback; postmortem | BE
R-13 | Test environment khác production → bug không reproduce (MỚI) | Quality | Medium | Medium | 6 | Staging gần prod nhất có thể; same data shape; same configs | Production smoke test 15 min sau deploy | BE

## Decision Log
Decision Log — quyết định kỹ thuật/business quan trọng
ID | Ngày | Lĩnh vực | Quyết định | Lý do / Trade-off | Người quyết | Tác động
D-001 | — | Tech | Backend: FastAPI | FastAPI: dev nhanh, AI mạnh | Tech Lead | Áp dụng Sprint 1+
D-002 | — | Tech | Realtime: WebSocket vs Polling 1s | Polling đơn giản, đủ 200ms target. | Tech Lead | Frequency picker
D-003 | — | Scope | Payment: P1 placeholder, P2 thật | Compliance Stripe JP phức tạp; validate product trước. | PM + Sponsor | Premium flow
D-004 | — | Product | Free tier: 3 lần chơi/ngày, 3 số picker, 1 saved | Cân bằng hooked user vs lý do upgrade. | PM | Conversion rate
D-005 | — | i18n | Ship VI + JA P1, EN slip P2 | EN không target chính; tiết kiệm 1 tuần. | PM | Sprint 4 scope
D-006 | — | QA | Test automation > 60% (MỚI) | PM kiêm QA → automation là bắt buộc, không phải optional. | PM | Sprint 1+
D-007 | — | QA | Coverage target: BE > 70%, FE > 60% (MỚI) | Realistic cho team 3 người + dùng AI assist. | Tech Lead | DoD enforce

## Weekly Report
Weekly Status Report — gửi manager mỗi thứ Sáu
Tuần | [VD: Tuần 3 (10/06–14/06)]
Sprint | [VD: Sprint 2 — Tuần 1/2]
PM | [Tên PM]
Overall Health | 🟢 Green / 🟡 Yellow / 🔴 Red
✅ HIGHLIGHTS — Đã làm được trong tuần
• [VD] Hoàn thành Auth: register, login, JWT, forgot password — unit test pass 85%.
• [VD] Crawler chạy auto 3 ngày liên tục, 0 lỗi.
• [VD] Frequency engine perf test baseline: P95 = 180ms ✓ (target 200ms).
⚠️ LOWLIGHTS / ISSUES
• [VD] FE delay 1 ngày do Figma chưa hoàn thiện picker — đã catch up.
• [VD] 2 bug P2 phát hiện trong bug bash — đã assign, fix tuần sau.
• [VD] Crawler fail 1 lần ngày 12/06 do Mizuho đổi HTML — đã fix.
📊 METRICS — auto từ Sprint Backlog
Metric | Giá trị | Target | Status
Story points tổng dự án | 214 | —
Story points đã done | 0 | —
% Done toàn dự án | 0% | Theo tuần
Story points done tuần này (điền tay)
Bug count: P1 / P2 / P3 | 0 / 0 / 0 | 0 P1, ≤ 3 P2
Defect leak rate (UAT bugs / total bugs) |  | < 5%
Code coverage (BE / FE) |  | BE > 70%, FE > 60%
Crash-free sessions |  | > 99%
🚨 TOP RISKS — Cập nhật tuần này (chi tiết ở Risk Log)
• [VD] R-02 Frequency performance — đang ổn định ở P95 = 180ms, theo dõi tiếp.
• [VD] R-11 PM kiêm QA bottleneck — automation đã đạt 65%, on track.
🤝 QUYẾT ĐỊNH CẦN STAKEHOLDER
• [VD] Có thêm feature X vào P1 hay đẩy P2? Cần chốt thứ Hai tuần sau.
📅 NEXT WEEK — Mục tiêu tuần tới
• [VD] Hoàn thành Frequency engine + Redis cache.
• [VD] FE: Real-time counter trong picker.
• [VD] Chuẩn bị demo nội bộ cuối tuần với anh Hùng.
• [VD] Bug bash 1 buổi thứ Năm.